## Question 1
1
|  |  | A | 4 |  |  | D | 4
|  |  | 0 | 4 |  |  | 4 | 8
|  |  | 0 | 4 |  |  | 11 | 15 | G | 2
[5 empty] | C | 3 |  |  | 15 | 17
[5 empty] | 4 | 7 |  |  | 15 | 17 |  | Completion time
| Start |  |  |  | 4 | 7 | E | 8 |  |  | End | 17
[7 empty] | 7 | 15
|  |  | B | 6 |  |  | 7 | 15
|  |  | 0 | 6
|  |  | 1 | 7
[5 empty] | F | 7 | H | 1
[5 empty] | 6 | 13 | 13 | 14
[5 empty] | 9 | 16 | 16 | 17
| Critical path: | A,C,E,G

## Question 2
2 |  | a | m | b
a | Activity | Optimistic | Likely | Pessimistic |  | Mean (t) | Variance
| A | 3 | 6 | 6 |  | 5.5 | 0.25
| B | 5 | 8 | 11 |  | 8 | 1
| C | 5 | 6 | 10 |  | 6.5 | 0.69444
| D | 1 | 2 | 6 |  | 2.5 | 0.69444
| E | 7 | 11 | 15 |  | 11 | 1.7778
| F | 7 | 9 | 14 |  | 9.5 | 1.3611
| G | 6 | 8 | 10 |  | 8 | 0.44444
| H | 3 | 4 | 8 |  | 4.5 | 0.69444
| I | 3 | 5 | 7 |  | 5 | 0.44444
|  |  |  | A | 5.5 |  | B | 8 | D | 2.5 | E | 11 |  |  | I | 5 | completion time
|  |  |  | 0 | 5.5 |  | 5.5 | 13.5 | 13.5 | 16 | 16 | 27 |  |  | 30 | 35 | Finish | 35
|  |  |  | 0 | 5.5 |  | 5.5 | 13.5 | 13.5 | 16 | 19 | 30 |  |  | 30 | 35
|  |  |  | slack | 0 |  | slack | 0 | slack | 0 | slack | 3 |  |  | slack | 0
b | Start | [5 empty] | C | 6.5 |  |  | F | 9.5 | H | 4.5
[7 empty] | 5.5 | 12 |  |  | 16 | 25.5 | 25.5 | 30
[7 empty] | 7 | 13.5 |  |  | 16 | 25.5 | 25.5 | 30
[7 empty] | slack | 1.5 |  |  | slack | 0 | slack | 0
[11 empty] | G | 8
[11 empty] | 16 | 24
| Critical path: A,B,D,F,H,I | [9 empty] | 17.5 | 25.5
[11 empty] | slack | 1.5
c | Probability to complete in 34 days or less
|  |  | = | 4.4444
|  |  | = | 2.1082 | days
=(35 days -34 days) / 2.108
0.47434
lookup from normal table
|  |  | 0.68082 | 0.31918 | (1-normal table value)
d | The probability of completing the project in 29 days or more
(35 - 29) / 2.108
2.846
lookup from normal table
0.99781
Project variance = ∑variances of activities on the critical path

## Question 3
3
|  |  | A | 3 |  |  | C | 6 |  | F | 2
|  |  | 0 | 3 |  |  | 3 | 9 |  | 9 | 11
|  |  | 0 | 3 |  |  | 4 | 10 |  | 10 | 12 | H | 5 | completion time
[12 empty] | 12 | 17 | End | 17 | weeks
Start | [11 empty] | 12 | 17
[7 empty] | E | 5 |  | G | 4
|  |  | B | 4 |  |  | 3 | 8 |  | 8 | 12
|  |  | 0 | 4 |  |  | 3 | 8 |  | 8 | 12
|  |  | 2 | 6
[7 empty] | D | 2
[7 empty] | 4 | 6
[7 empty] | 6 | 8
Critical path: A,E,G,H
|  |  | Normal time | Crash time | Normal cost | Crash cost | crash cost/time period | Critical?
| A | - | 3 | 2 | 8000 | 9800 | 1800 | Y
| B | - | 4 | 3 | 9000 | 10000 | 1000
| C | A | 6 | 4 | 12000 | 15000 | 1500
| D | B | 2 | 1 | 15000 | 15500 | 500
| E | A | 5 | 3 | 5000 | 8700 | 1850 | Y
| F | C | 2 | 1 | 7500 | 9000 | 1500
| G | D,E | 4 | 2 | 8000 | 9400 | 700 | Y | smallest crash cost per week
| H | F,G | 5 | 3 | 5000 | 6600 | 800 | Y
Crash G with one week
Total cost of this is 700
|  |  | A | 3 |  |  | C | 6 |  | F | 2
|  |  | 0 | 3 |  |  | 3 | 9 |  | 9 | 11
|  |  | 0 | 3 |  |  | 3 | 9 |  | 9 | 11 | H | 5 | completion time
[12 empty] | 11 | 16 | End | 16 | weeks
Start | [11 empty] | 11 | 16
[7 empty] | E | 5 |  | G | 3
|  |  | B | 4 |  |  | 3 | 8 |  | 8 | 11
|  |  | 0 | 4 |  |  | 3 | 8 |  | 8 | 11
|  |  | 2 | 6
[7 empty] | D | 2
[7 empty] | 4 | 6
[7 empty] | 6 | 8
There are now two critical paths:
A,C,F,H and A,E,G,H, each 16 weeks
And a non-critical path B,D,G,H
|  |  | Normal time | Crash time | Normal cost | Crash cost | crash cost/time period | Critical?
| A | - | 3 | 2 | 8000 | 9800 | 1800 | Y
| B | - | 4 | 3 | 9000 | 10000 | 1000
| C | A | 6 | 4 | 12000 | 15000 | 1500 | Y
| D | B | 2 | 1 | 15000 | 15500 | 500
| E | A | 5 | 3 | 5000 | 8700 | 1850 | Y
| F | C | 2 | 1 | 7500 | 9000 | 1500 | Y
| G | D,E | 3 | 2 | 8700 | 9400 | 700 | Y
| H | F,G | 5 | 3 | 5000 | 6600 | 800 | Y
To crash another week, G alone won't help as there is another critical path
Crashing either H or A will reduce both paths with one week and the cost is lowest for H